# If you impose AI, your team slows it down: the 4-week plan

For anyone who must "roll out AI" to a team that did not ask for it and would rather they take part than obey.

# When to use it

- You were assigned to "bring AI" to your area and the start date is already set.

- You announced a tool, the room went quiet and nobody opened it afterwards.

- A previous attempt stalled on its own, without anyone saying no.

# The sheet

When you say "we are going to use AI", many do not hear "productivity"; they hear "cuts". If you do not talk about that, fear fills the silence. This plan starts there.

| Week | Objective | Activity | Signal of progress | The mistake that makes the team slow it down |
| --- | --- | --- | --- | --- |
| 1 · The why | The team knows which problem you want to solve and where the freed time goes. | 30-minute meeting. You name the problem with a number (illustrative: "quotes take three days"). You say honestly where the freed time goes. | Someone asks a hard question out loud. | Showing the tool before explaining the why. |
| 2 · They choose | The team picks the first task to improve. | Each person writes down what eats their time. They vote for one task. You do not vote. | The chosen task is not the one you would have chosen. | Choosing the task for them "to move faster". |
| 3 · The trial | Try the AI on that task, with a before number. | Two or three people use it on real work and note where it helped and where it failed. | There is a documented mistake and nobody hid it. | Measuring people instead of the task. |
| 4 · The review | Decide together: keep, adjust or stop, and pick the next task. | 30-minute meeting. Before and after number. You honor what you said in week 1 about the freed time. | The team proposes the second task without being asked. | Declaring success without a number, or changing where the freed time goes. |

Problem we are going to solve: ____________ · The freed time will be used for: ____________ · Task chosen by the team: ____________

# How to fill it in 15 minutes

- Fill in the line "the freed time will be used for" first. If you cannot write it honestly, do not start yet.

- Write the problem with a number, even an approximate one marked as such. "Improve productivity" is not a problem; it is a phrase.

- Leave the week 2 task blank. The team fills it in; that is what makes them actually use the tool.

- Plan week 3 with two or three people. A small trial with a visible mistake teaches more than a general launch.

- The most common mistake: skipping week 1 because "everyone already knows why". They do not. If they only receive the order, they look for ways not to use it.

# The line that is almost always missing

The week 1 promise about the freed time, honored in week 4. The team agrees to try because you told them where that time would go. If in week 4 it goes elsewhere, the next plan never starts, however good it is. If the team helps decide, they use it; if they only receive the order, they slow it down.

# If this becomes a big decision

If the plan means buying licenses for the whole area or changing roles, the free tools at vicsol.org/decision-clarity/ help you structure the decision. They do not replace a formal review.