## Template
Field | What to write | Illustrative example
What we expected | The number or result the original proposal promised, copied word for word. | "Quotes from 3 days to 1 in 8 weeks."
What happened | The actual number, with a date. No adjectives. | "Week 8: 2.5 days. Week 12: 2 days."
Which signal we ignored | The data point that was in plain sight before it became obvious, and when it was first seen. | "Week 3: only 2 of 9 reps were using the draft."
What we keep | What worked and stays, even if the initiative changes. | "The quote template and the single reviewer."
What changes next time | One concrete rule for the next initiative, not an intention. | "No pilot starts without a user from the area from day 1."
Who owns the change | One named person and the date the rule takes effect. | "Laura (sales), from the next pilot, 1 March."

## About
Title | Lessons learned from an AI initiative (without blame)
Source | Vic Sol · Decision Desk
Page | https://vicsol.org/resources/lecciones-aprendidas-iniciativa-ia/
Updated | 2026-10-19
How to use it | Yellow-shaded cells are fields to fill in. The first row stays frozen as you scroll.
Note | Vic Sol · Decision Desk · vicsol.org/resources/ · Free to use with attribution.
This sheet structures a conversation; it is not legal, financial or audit advice.