## Template
Stage | Objective | Deliverable | Metric | Who reviews it
Days 1–30: understand | Know what is used today, with which data, and what the chosen process costs. | Inventory of tools in use, a baseline for one process and minimum usage rules in writing. | Inventory complete (yes/no); baseline measured with a source. | [director or committee]
Days 31–60: test | Test a single use case with a metric defined before it starts. | One scoped pilot: scope, participants, start and end date. | The baseline metric, measured again when the pilot closes. | [process owner]
Days 61–90: decide | Decide with evidence whether to continue, adjust or switch off. | One-page memo: result, real cost, what did not work and the decision. | Decision made and recorded on time (yes/no). | [director or committee]

## About
Title | Your 30-60-90 AI plan as a manager (without promising what you don't control)
Source | Vic Sol · Decision Desk
Page | https://vicsol.org/resources/plan-30-60-90-ia/
Updated | 2026-10-19
How to use it | Yellow-shaded cells are fields to fill in. The first row stays frozen as you scroll.
Note | Vic Sol · Decision Desk · vicsol.org/resources/ · Free to use with attribution.
This sheet structures a conversation; it is not legal, financial or audit advice.