## Template
# | Risk | Early signal | Likelihood | Impact | Owner | Response | Review date
1 | AI answers with outdated or incomplete data. [Illustrative.] | Two client complaints about the same answer in one week. | M | H | Head of operations | Reduce: weekly sample review; documented data cut-off. | __/__
2 | The team stops reviewing what AI produces. [Illustrative.] | Review time per item drops to zero in the log. | H | M | Area lead | Reduce: mandatory sample; whoever sends, signs. | __/__
3 | The vendor changes price or terms mid-contract. [Illustrative.] | Notice of change of terms; a "new plan" email. | L | H | Procurement or legal | Transfer: exit clause and data export. | __/__
4
5

## About
Title | Risk register and operating readiness for an AI initiative
Source | Vic Sol · Decision Desk
Page | https://vicsol.org/resources/registro-riesgos-y-readiness/
Updated | 2026-10-19
How to use it | Yellow-shaded cells are fields to fill in. The first row stays frozen as you scroll.
Note | Vic Sol · Decision Desk · vicsol.org/resources/ · Free to use with attribution.
This sheet structures a conversation; it is not legal, financial or audit advice.